BMI Brain: work beyond the original specification

Cybix for BMI Publishing · Scope summary · October 2026

1. What the original specification covered

The specification of 9 July 2026 ("The Sales & Data Brain, Option 2") was a set of automations built in n8n on top of BMI's existing Act! CRM. Act! stayed the system of record; the work was the automations, plus a simple screen for reviewing what they suggest. It was quoted at about 112–173 developer-days across five workstreams:

Foundation (10–16 days): the Act! connection, AI, email and Teams links, and a review queue.

Stage 1, Clean foundation (22–35): bounces, out-of-office replies, departures, duplicates, returned copies, business cards.

Stage 2, Living memory + AI chat (21–32): call notes, proposal logging, email summaries, inbound contacts, and an AI chat over the CRM.

Stage 3, Daily engine (23–35): follow-up triggers, the morning queue, personal touchpoints, proposal drafting, renewals, templates, meeting notes → pitch.

Stage 4, Reporting (17–26): prospect pipeline, chase lists, sales dashboard, delivery tracking, and the weekly management summary.

It assumed BMI's sales data stayed in the Sales Order Register spreadsheets and Act!. The SOR and Xero were only to be read from.

2. What we built on top of that, and how it helps BMI

Following BMI's feedback (the Act! user feedback, the sales team's requests and the 8 October meeting), the work grew from automations into a complete CRM and sales system that replaces Act! and the SOR spreadsheets. None of the items below were in the specification.

| Addition | What it is and why it helps BMI |
| --- | --- |
| Our own CRM, replacing Act! | Contacts, companies, groups, activities, reminders, roles and database access, with Act! data migrated. No Act! licences, Web API or server dependency; built around how BMI works. |
| Search, import, bulk update, export | Search on every field, advanced filters, Excel/PDF contact import with automatic column matching, bulk update with preview and undo, Excel export, copy emails. |
| Mail merge and email templates | Outlook, Word letters, labels and data files; a template library by brand and purpose, with brand facts and issue details filled in. Clare's 7 ACT templates were loaded. |
| Sales Order Register in the system | Every booking across 15+ spreadsheets in one place: editions, bookings, filters, renewals and invoicing. Replaces the SOR workbooks. |
| Orders and order confirmations | Multi-item orders (campaigns across issues, events and digital), discounts, agency commission, pencilled/confirmed status, BMI-style confirmation documents emailed from Outlook, and rebooking for next year. |
| Accounts check on orders | Credit control checks the client, CRM company, addresses and items before a confirmation goes out (Matt's safeguard). |
| Xero link and invoice matching | Hourly read-only Xero sync, paid/unpaid/overdue on every booking, automatic invoice-to-booking matching with a review queue, "Not a booking" handling. |
| Commission engine and statements | Per-person plans, the new-business rules (24 months, first invoice), bonuses, event profit share with cost sign-off, attendance bonus, PAYE/advances payout, monthly statements and Excel. |
| Rate card | Every brand's prices by section, sizes and page counts, brand-own sections (cover wraps, belly bands), offers, price history, next-year copy, used by orders, proposals and renewals. |
| Editorial plan | Issue dates, deadlines and features for every title, deadline reminders, and "who should we pitch" lists. |
| Costs and profit | Costs on any issue, event or awards (parts, budgets, per-booking costs) and a profit report across editions. |
| Reporting extras | Financial-year (July–June) views, booked vs invoiced comparisons, any-two-editions comparison, a per-salesperson weekly summary. |
| Admin controls | Admin-only settings, and hiding sections per role or per person to keep screens simple. |
| Richer proposals | Several titles and issues, options A/B, line and total discounts, proposal types, Word output with branding, sending from Outlook, and turning a proposal into an order. |

3. What is still to do

From the original specification:

SALES-008 call notes: needs Teams/Zoom transcripts from BMI.

SALES-009 proposal detection from sent mail: a first version (logging when a proposal is sent) is built; reading sent mail needs IT access.

SALES-022 template library + save-the-sale replies: the template library is built; the save-the-sale responses remain.

SALES-023 meeting notes → pitch, and the AI Hub chat: planned together as one AI phase.

SALES-024 prospect pipeline → SALES-025 chase lists: need the reps' current pipeline spreadsheets.

SALES-027 sold-work delivery tracking: needs BMI's delivery stages and expected timings.

Additional work agreed but not yet built (outside the specification):

Proposal AI: drafting full proposals in each salesperson's style from past proposals, with a proposal library (planned; ~15–24 days, of which ~10–18 is beyond the spec).

Act! feedback #7: when a company's address changes, offer to update its contacts.

Go-live work: final Act! data migration, the latest SOR sheets, live Xero and Outlook connection, testing with the team, and a performance pass.

Waiting on BMI: Microsoft Outlook permissions from IT, an automation@ mailbox, updated SOR sheets, rate card and editorial plan checks (Clare and production), weekly summary KPIs (Matt), Xero account details, and example contacts for the custom Act! fields.

4. Basis for additional billing

Everything in section 2 sits outside the quoted 112–173 days. Its largest part is the CRM itself, which the specification assumed Act! would provide. We propose billing it as a change request at the agreed day rate, with the still-to-do items from section 3 quoted separately once BMI provides the inputs listed.